## UAT Overview
AeroCargo user acceptance testing
Execution summary | Count
Total cases | 24
Pass | 0
Fail | 0
Blocked | 0
Not Run | 24
Not Applicable | 0
Execution progress | 0%
Purpose | Confirm that a freight-forwarder user can enter cargo, request sample quotes and complete the demo booking journey.
Build under test | aerocargo_python_backend.zip; record your local build/version before execution.
Local build / version
Environment | Python 3.9+; python server.py; browser at http://127.0.0.1:8000; Swagger at /docs.
Tester / browser
Entry criteria | Server starts; demo portal loads; test data available; candidate cases and acceptance criteria reviewed.
Scope | Customer portal, importer, calculations, validation, review, submission, sample quotes, demo booking, browser history, backend persistence.
Scope limits | Login is simulated; quotes and bookings are demos. No live airlines, payments, real AWBs, multi-user security or admin portal acceptance.
Execution method | Record actual results, evidence, tester and date. Mark Pass only after observing expected behavior. Log failures in Defects; retest after fixes.
Status rules | Blocked = unable to execute. Not Applicable requires a reason in Actual result and owner agreement. Blank results are not acceptance evidence.
Proposed exit criteria | All applicable cases executed; all High-priority cases pass; no open Critical/High defects; remaining issues and exclusions accepted by the business owner. Confirm these criteria before testing.
UAT decision | Pending
Business approver / role
Sign-off date
Accepted exceptions / reasons
Evidence reviewed
Basis | Prepared from the supplied AeroCargo Python prototype and visible shipment workflow. These are proposed UAT cases, not signed business requirements.
Result status | No user UAT execution evidence has been verified. Developer/API checks do not constitute business acceptance.

## UAT Cases
AeroCargo UAT cases
Execute in order using the Python app. Amber cells are for tester input. All cases start Not Run.
UAT ID | Area | Business scenario | Priority | Preconditions / data | Test steps | Expected business result | Actual result | Status | Evidence / request ID | Defect ID | Tester | Execution date | Retest notes
UAT-01 | Access | Open the customer portal | High | Python server running; browser open. | 1. Open http://127.0.0.1:8000. 2. Enter test@example.com and a nonempty password. 3. Select Sign In. | Cargo request page opens. Demo login is clearly identified. No real account authentication is implied. |  | Not Run
UAT-02 | Importer | Start with an empty importer | High | Fresh sign-in; no text pasted. | 1. Locate Shipment Importer. 2. Click inside the box. | Box contains no prefilled shipment text and accepts typing/pasting. Other form defaults are not required to be blank. |  | Not Run
UAT-03 | Importer | Autofill a complete shipment | High | Signed in; Test Data provides TD-01. | 1. Copy TD-01 shipment text. 2. Paste into Shipment Importer. 3. Wait for autofill. 4. Compare each form field with TD-01. | Pickup, destination, date, cargo type, known shipper, commodity, units, gross mode, 2 pieces, 48 × 40 × 45 dimensions and 1150 lb fill correctly. Handling is Yes. |  | Not Run
UAT-04 | Importer | Import non-stackable and unknown shipper | High | Fresh request; TD-01 available. | 1. Change Known Shipper to No and Handling / Packing to No in pasted TD-01. 2. Wait for autofill. | Known Shipper and Handling / Packing both show No. Negative values are not interpreted as Yes. |  | Not Run
UAT-05 | Importer | Handle incomplete shipment text | High | Signed in. | 1. Paste only: Gross Weight: 100 kg. 2. Inspect the importer message and cargo row. 3. Try Search Rates. | Missing dimensions are blank and identified for manual entry. Search Rates does not proceed until dimensions are provided. |  | Not Run
UAT-06 | Importer | Handle unrelated pasted text | Medium | Record current form values. | 1. Replace importer text with: Hello, please call me. 2. Wait for response. | No shipment details recognized message appears. Unrelated text does not invent shipment values. |  | Not Run
UAT-07 | Importer | Retain manual corrections | High | TD-01 imported successfully. | 1. Change destination manually from MAA to DEL. 2. Select Search Rates. 3. Inspect route on review page. | Review shows DEL. A manual correction remains effective without another paste. |  | Not Run
UAT-08 | Importer | Clear text without losing form edits | Medium | TD-01 imported; manual destination changed to DEL. | 1. Delete all text from importer. 2. Inspect destination and cargo row. | Importer becomes blank. Existing form values, including DEL, remain available. |  | Not Run
UAT-09 | Cargo | Calculate gross-mode totals | High | TD-01 imported. | 1. Confirm gross mode and 2 pieces. 2. Inspect displayed totals. | Total pieces = 2; gross = 1150.0 lb; volume = 472.1 lb; chargeable = 521.6 kg. Values are rounded to one decimal. |  | Not Run
UAT-10 | Cargo | Calculate piece-mode totals | High | Start with TD-01. | 1. Select piece mode. 2. Set weight to 575 lb per piece. 3. Keep 2 pieces and existing dimensions. | Total gross stays 1150.0 lb and chargeable stays 521.6 kg. Piece weight is multiplied by quantity once. |  | Not Run
UAT-11 | Cargo | Calculate metric-unit shipment | High | Fresh request; TD-02 available. | 1. Paste TD-02. 2. Confirm cm and kg units. 3. Inspect totals. | 1 piece, 100 × 80 × 60 cm and 100 kg are populated. Gross = 220.5 lb and chargeable = 100.0 kg under the current demo divisor. |  | Not Run
UAT-12 | Cargo | Add and remove a cargo row | High | TD-01 imported. | 1. Select Add More Cargo. 2. Add 1 piece, 10 × 10 × 10 in, gross 100 lb. 3. Inspect totals. 4. Remove that row. | After adding: 3 pieces and 1250.0 lb gross. After removal: 2 pieces and 1150.0 lb. Original row remains unchanged. |  | Not Run
UAT-13 | Validation | Require a drop-off date | High | TD-01 imported. | 1. Clear expected drop-off date. 2. Select Search Rates. | User stays on cargo page and sees an instruction to enter a drop-off date. |  | Not Run
UAT-14 | Validation | Reject non-positive cargo values | High | TD-01 imported. | 1. Set weight to 0 and select Search Rates. 2. Repeat with weight -5. 3. Restore weight; repeat with pieces 0 and length 0. | Each invalid attempt is blocked. No request can be submitted with the invalid cargo value. |  | Not Run
UAT-15 | Review | Review and edit shipment details | High | Complete TD-01 entered. | 1. Select Search Rates. 2. Compare cargo details and totals. 3. Select Edit; change commodity to Electronics. 4. Return to review. | Review accurately reflects the shipment and the corrected commodity. Entered values survive navigation. |  | Not Run
UAT-16 | Submission | Require acceptance of demo terms | High | Review page; terms unchecked. | 1. Select Submit Request without accepting terms. | A message requests acceptance. User remains on review and no request is submitted by this action. |  | Not Run
UAT-17 | Submission | Submit request and receive quotes | High | Valid shipment on review page. | 1. Enter reference UAT-REF-001. 2. Accept terms and submit. 3. Record the displayed request ID as the execution reference. | Request saves successfully and two sample airline quotations display. A shipment UUID is shown. Quotes are marked as demo/sample rates. |  | Not Run
UAT-18 | Quotes | Compare quotations and inspect costs | High | UAT-17 completed. | 1. Compare Qatar Airways and Air India. 2. Open each View Quote page. 3. Compare components with total. | Both quotes show positive USD amounts. Airline plus inland cost equals total, allowing displayed rounding. Route uses the submitted destination. |  | Not Run
UAT-19 | Services | Exclude pickup charges | High | Fresh TD-01 request. | 1. Select Air Freight Only. 2. Review, accept terms and submit. 3. Open quote detail. | Inland service cost is zero/excluded. Quote total reflects airline charges without pickup-related charges. |  | Not Run
UAT-20 | Booking demo | Complete simulated booking | High | Quote detail open after UAT-17. | 1. Select Book Quote. 2. Inspect confirmation and reference. | Demo Booking Complete appears, with a DEMO-prefixed AWB and UAT-REF-001. No real airline booking or real AWB issuance is claimed. |  | Not Run
UAT-21 | History | Find booking in browser history | Medium | UAT-20 completed in the same browser. | 1. Open Request History. 2. Locate the request ID from UAT-17. 3. Refresh, sign in and reopen history. | Simulated booking remains listed with matching route, airline and amount. This history is browser-local, not the API shipment list. |  | Not Run
UAT-22 | Metrics | Reflect the completed demo booking | Medium | Record booking count before running UAT-20. | 1. Open Metrics after UAT-20. 2. Compare booking count and value with the new booking. | Booking count increases by one and total demo value increases by that booking amount in the same browser. |  | Not Run
UAT-23 | Persistence | Retain saved shipment after restart | High | UAT-17 completed; shipment ID recorded. | 1. Stop Python server and restart python server.py. 2. In Swagger GET /api/shipments/{id}, enter recorded ID and Execute. | 200 response returns the same saved shipment details. This verifies backend persistence, independent of browser booking history. |  | Not Run
UAT-24 | Error handling | Explain an unavailable backend | High | Portal loaded with backend running. | 1. Stop backend. 2. Paste TD-01 into importer. 3. Observe message. 4. Restart backend and paste again. | Failure is visible; no successful import is claimed while offline. After restart, a new paste fills the form. |  | Not Run

## Test Data
Test data and calculation reference
Data ID | Input / instruction | Expected / purpose
TD-01 | Pickup Address: CA 90046 Origin: LAX Destination: MAA Expected Drop Off: 25-10-2026 Cargo Type: General Cargo Known Shipper: Yes Commodity: Textiles & Fashion Weight Mode: gross Units: in / lb Pieces: 2 Length: 48 Width: 40 Height: 45 Gross Weight: 1150 lb Handling / Packing: Yes | Baseline: 2 pieces; total gross 1150 lb; dimensions per piece. Paste only column B text.
TD-02 | Pickup Address: CA 90046 Origin: LAX Destination: MAA Expected Drop Off: 25-10-2026 Cargo Type: General Cargo Known Shipper: Yes Commodity: Textiles & Fashion Weight Mode: gross Units: cm / kg Pieces: 1 Length: 100 Width: 80 Height: 60 Gross Weight: 100 kg Handling / Packing: Yes | Metric shipment. Paste only column B text.
Reuse data | Use a fresh sign-in/request as specified. Record each new request UUID in the case evidence column. | Dates are illustrative. Use a suitable future date if executing later; preserve format.
Reference | Value | Calculation / convention
Pieces | 2 | TD-01 quantity
Length (in) | 48 | Per piece
Width (in) | 40 | Per piece
Height (in) | 45 | Per piece
Gross weight (lb) | 1150 | Total row weight in gross mode
Cubic inches per lb | 366 | Current prototype divisor; not a universal carrier rule
lb per kg | 2.2046 | Current prototype conversion
Volume weight (lb) | 472.1311
Chargeable weight (kg) | 521.6312
Rounding tolerance | 0.1 | Use displayed one-decimal totals; cost comparisons allow USD 0.02 for summed rounded components.
Scope notes | Browser history stores demo bookings; the API stores shipments. | Do not treat these as the same record list.
Sources | AeroCargo Python app: server.py, shipment_importer.py, app.js, README.md. | Test design based on current prototype behavior and user-requested importer workflow.

## Defects
UAT defect log
Blank log: enter only observed issues. Link each issue to its UAT ID and capture retest evidence.
Defect ID | UAT ID | Issue title | Reproduction steps | Expected result | Actual result | Severity | Status | Owner | Evidence | Retest result | Resolution / accepted exception